## TASKS
WEEKLY TASK SCHEDULE CALANDER - Question - Answering (QA) System Using PubMed Data
START DATE | MY TASKS | MEMBER | % COMPLETE | NOTES
2023-11-01 | Dataset Extraction | Vishal Mangukiya | 25%
2023-11-02 | Dataset Extraction | Vishal Mangukiya | 25%
2023-11-05 | Dataset Extraction | Vishal Mangukiya | 50%
2023-11-10 | Dataset Extraction | Vishal Mangukiya | 75%
2023-11-11 | Dataset Extraction | Vishal Mangukiya | 75%
2023-11-12 | Dataset Extraction | Vishal Mangukiya | 100%
2023-11-13 | Dataset Extraction | Vishal Mangukiya | 100% | Done
2023-11-14 | Different methods used for Data extraction | Radha Mungara | 0% | -
2023-11-16 | Different methods used for Data extraction | Radha Mungara | 25%
2023-11-20 | Different methods used for Data extraction | Radha Mungara | 50%
2023-11-21 | Different methods used for Data extraction | Radha Mungara | 75%
2023-11-22 | Different methods used for Data extraction | Radha Mungara | 75%
2023-11-28 | Different methods used for Data extraction | Radha Mungara | 100%
2023-11-29 | Different methods used for Data extraction | Radha Mungara | 100% | Done
2023-11-30 | Data retreival techniques | Radha Mungara | 25%
2023-12-01 | Data retreival techniques | Radha Mungara | 25%
2023-12-08 | Data retreival techniques | Radha Mungara | 25%
2023-12-09 | Data retreival techniques | Radha Mungara | 50%
2023-12-10 | Data retreival techniques | Radha Mungara | 75%
2023-12-11 | Data retreival techniques | Radha Mungara | 100%
2023-12-12 | Data retreival techniques | Radha Mungara | 100% | Done
2023-12-13 | Research complete (collect research paper) | Radha Mungara & Mangukiya Vishal | 25%
2023-12-14 | Research complete (collect research paper) | Radha Mungara & Mangukiya Vishal | 50%
2023-12-15 | Research complete (collect research paper) | Radha Mungara & Mangukiya Vishal | 50%
2023-12-25 | Research complete (collect research paper) | Radha Mungara & Mangukiya Vishal | 75%
2023-12-26 | Research complete (collect research paper) | Radha Mungara & Mangukiya Vishal | 75%
2023-12-27 | Research complete (collect research paper) | Radha Mungara & Mangukiya Vishal | 100% | Done
2023-12-28 | Research in different techniques in data vectorization | Vishal Mangukiya | 25%
2023-12-29 | Research in different techniques in data vectorization | Vishal Mangukiya | 50%
2023-12-30 | Research in different techniques in data vectorization | Vishal Mangukiya | 50%
2024-01-05 | Research in different techniques in data vectorization | Vishal Mangukiya | 75%
2024-01-06 | Research in different techniques in data vectorization | Vishal Mangukiya | 75%
2024-01-08 | Research in different techniques in data vectorization | Vishal Mangukiya | 100% | Done
2024-01-09 | Researching about langchain model | Renuka Sahani and Suraj Desai | 0%
2024-01-10 | Researching about langchain model | Renuka Sahani and Suraj Desai | 25%
2024-01-11 | Researching about langchain model | Renuka Sahani and Suraj Desai | 75%
2024-01-12 | Researching about langchain model | Renuka Sahani and Suraj Desai | 100% | Done
2024-01-13 | Researching about llama and Open AI | Renuka Sahani and Suraj Desai | 25%
2024-01-14 | Researching about llama and Open AI | Renuka Sahani and Suraj Desai | 50%
2024-01-15 | Researching about llama and Open AI | Renuka Sahani and Suraj Desai | 75%
2024-01-16 | Researching about llama and Open AI | Renuka Sahani and Suraj Desai | 100% | Done
2024-01-17 | Researching about pinecone | Renuka Sahani and Suraj Desai | 100% | Done
2024-01-18 | Model 1 LLM(data from website) Implementation | Radha Mungara & Vishal Mangukiya | 0%
2024-01-21 | Model 2 QA_System_OpenAI Implementation | Renuka Sahani and Suraj Desai | 25%
2024-01-22 | Model 1 LLM(data from website) Implementation | Radha Mungara & Vishal Mangukiya | 25%
2024-01-23 | Model 2 QA_System_OpenAI Implementation | Renuka Sahani and Suraj Desai | 25%
2024-01-30 | Model 1 LLM(data from website) Implementation | Radha Mungara & Vishal Mangukiya | 25%
2024-02-02 | Model 2 QA_System_OpenAI Implementation | Renuka Sahani and Suraj Desai | 25%
2024-02-03 | Model 1 LLM(data from website) Implementation | Radha Mungara & Vishal Mangukiya | 25%
2024-02-05 | Model 2 QA_System_OpenAI Implementation | Renuka Sahani and Suraj Desai | 50%
2024-02-06 | Model 1 LLM(data from website) Implementation | Radha Mungara & Vishal Mangukiya | 50%
2024-02-07 | Model 2 QA_System_OpenAI Implementation | Renuka Sahani and Suraj Desai | 75%
2024-02-08 | Model 1 LLM(data from website) Implementation | Radha Mungara & Vishal Mangukiya | 50%
2024-02-09 | Model 2 QA_System_OpenAI Implementation | Renuka Sahani and Suraj Desai | 100% | Done
2024-02-10 | Model 1 LLM(data from website) Implementation | Radha Mungara & Vishal Mangukiya | 75%
2024-02-11 | Model 3 LLM(with UI) Implementation | Renuka Sahani and Suraj Desai | 0%
2024-02-12 | Model 1 LLM(data from website) Implementation | Radha Mungara & Vishal Mangukiya | 75%
2024-02-13 | Model 3 LLM(with UI) Implementation | Renuka Sahani and Suraj Desai | 25%
2024-02-14 | Model 1 LLM(data from website) Implementation | Radha Mungara & Vishal Mangukiya | 100% | Done
2024-02-15 | Model 3 LLM(with UI) Implementation | Renuka Sahani and Suraj Desai | 25%
2024-02-26 | Model 3 LLM(with UI) Implementation | Renuka Sahani and Suraj Desai | 50%
2024-02-27 | Model 3 LLM(with UI) Implementation | Renuka Sahani and Suraj Desai | 75%
2024-02-28 | Model 3 LLM(with UI) Implementation | Renuka Sahani and Suraj Desai | 100% | Done
2024-02-29 | Report Preparation and Important File Management | All the Members | 50%
2024-03-01 | Report Preparation and Important File Management | All the Members | 75%
2024-03-02 | Report Preparation and Important File Management | All the Members | 100%
2024-03-03 | Github Commits | All the Members | 100% | Done
2024-03-04 | Submission | All the Members | 100% | Done